## implementation schedule
Deadline: |  | to-do 1 | to-do 2 | to-do 3 | to-do 4 | to-do 5
| implementation of the expense page | delete the time picker | make the date picker | add payment mode field dropdown | after the user clicks the submit button - the information should be sent to a database via SQLite | after the user clicks the submit, it should take him to the expenses page for that particular day
| implementation of the setting page | implement the budget setting page | make the layout according to the drawing | implement the alert builder for the button that changes the budget | show the dailybudget accordingly | Fix the monthly budget textview: 1) don't allow to put a whole bunch of zeros before the period 2) if the amount is entered starting with a period, reformat the textview so that it start with a 0. 3)reformat the dailybudget textview accordingly | learn how to use a regular expressions and apply them to my inputs , so that the user won't be able to enter a whole bunch of zeros. | make another "or'" statement in my regex for starting of the number with a "." | write JavaDocs for the budgetSettings class | merge the branch
| reformatting the code | reformat the packages | save the values for budgetSettings using sharedPreferences | write JavaDoc and comments
Sat June 28th | implementation of the budget setting page (15 hours left) | Currency field should be static. | implement the currency textview in the budget settings activity | find all of the world currencies and all their respective abbreviations | find a way how to extract information from a txt file | create a simple txt file with all of the countries and currencies listed in it | fix the File D:/coding/android/BudgetControl/app/src/main/res/raw/currencies.txt contains a path separator error | test http://www.vogella.com/tutorials/AndroidFileBasedPersistence/article.html#exercise_preferences_5 to see if it extracts the needed information | read the information into 3 separate arrays that will hold countries, names and symbols respectively | test whether 1 symbol will show-up correctly in the UI. | IF not - read about how to convert it to show correctly and convert it | create an Array of currency classes from the 3 separate arrays | create a standard listview to display the currency objects on the device | implement the button that will take you to the list of available currencies. | add this file to git | make the unicode symbols show up in the UI | Change the Currencies toString method for a better look of the listview | Create a custom listview using the array of currency classes using startActivityforresult and saving the needed key value pair that will be available for later access through the app | The search should implement a helper. | Once the currency is chosen it should take the user back to the budgetSettings activity with the result saved in the currency textview. | apply currency to everything once it is implemented. | write JavaDoc and comments | refactor code
| hours | [14 empty] | 4 hours +
Sun July 6th | implementation of the start up page (20 hours) | implement the three main buttons | implement the bar graphs for the day | implement the bar graph for the month | implement the text field that show either the person overdrafted or saved money | write JavaDoc and comments | refactor code
hours
Sun July 20th | implementation of the history/statistics page (40 - 50 hours) | implement two fragments - one for switching between day, months, years, another one for switching between expenses for the current period and statistics | implement the back and forth buttons for switching between days, switching between weeks and so on | in the expenses tab - show each expense | in the statistics page - first show the same thing that's on the startup page (if the person overdrafted, or saved money on the current day/week/month), then show the expenses divided up into categories in a listview and then below a pie chart depicting this. | write JavaDoc and comments | refactor code
Friday July 25th | making the design pretty for start-up page (5 - 10 hours)
Sun July 27th | making the design pretty for addExpensePage
Friday August 1st | making the design pretty for BudgetSettingsPage
Friday August 8th | Making the design pretty for the statistics Page
Wednesday August 20th | testing and fixing bugs
Monday September 1st | releasing the first version to google play | read this after release -- | http://habrahabr.ru/post/225459/ | http://habrahabr.ru/post/225459/

## features for later versions
version 1
pocket budget | implement an interface that will show the current status for today on the main screen in android | https://lh4.ggpht.com/o6hzr7Y9Ow7aSh0dIPBUWQmtp-M3qX-Wa4Qn6H81p6N737FRO71HgQN7gPssDRekuTI=h900-rw
pocket budget | set the currency and set the monthly budgets | https://lh4.ggpht.com/YqNK8Dj5EaSn8S8ac_JBYShvW1X1IRUq19n-1C7QBECFTUscThz85rhlCjN0bgHoGA=h900-rw
https://play.google.com/store/apps/details?id=com.angeloid.budgeting | showing how much is left in a line
https://play.google.com/store/apps/details?id=com.techahead.ExpenseManager | this type of start up page | https://play.google.com/store/apps/details?id=com.techahead.ExpenseManager
| this type of expense entering with save and reset button | https://lh5.ggpht.com/RlM3-L0oI2eCcO1J1BTMIUNom_vWbBMdTSrkL8xjcIRJOzZEPHUJRb4E28jnBMbgtig=h900-rw
| this type of page that will show expenses, only with a custom tab at the end that will allow to search specific dates, and categories | https://lh5.ggpht.com/Oxrtdp1cAlF7QGaUDvRsWp6HO00HmtvE3R1sdvMjr-yFkvtpPlMC8bAZLryCq5uuVCE=h900-rw
the point of the app is to show warning when the user is overdrafting or about to overdaft his balance
for later versions:
pocket budget | creating custom categories | https://lh5.ggpht.com/OXFYsV0AVxUvAZK7FnYS9lrqm23yNLWQvu8AfE4haP8ge3tE-RIxLYt9dIKJ6ZSxag=h900-rw
Daily Expense Manager (DEM) | allow to search specific dates, and categories in the fifth column | https://lh4.ggpht.com/_KHUQi4PKfmxHNBNOQnI7mkjPMSHGCoOnPUOVx8gbXA6J8Xw2hVT_fB4-QUID3W66klz=h900-rw
setting password and language
showing warnings, with red, green and other types of screen, when the user gets to a certain point of daily budget
В случае если бюджет за предыдущие дни был превышен и у юзера не было сохранненых денег – рядом с бюджетом будет показываться восклицательный знак, при нажатии на который будет вылазить окно запрашивающее изменить бюджет на последующие дни
Здесь, количество сохраненных денег цифрой за предыдущие дни. В случае овердрафта – размер овердрафта
reminder of how much a person can spend this day in a notifications bar in version 2
Add gamification to my application in future versions by showing which day/month you saved the most money in percentage
besides having custom categories that the user can add, and that will always be accessible like in Toshl, it is a good idea to have a an auto-complete for the description also.
Add a shortcut to notifications bar for adding an expense
the application should remind a person to enter expenses at some point in time
Create a widget for budgetControl
Add the option of being able to plan future expenses and and automatically prompting to modify the current daily budget in future versions

## startUp Page
money saved / lost this month so far (this is green if the money is saved from previous days - red, if the money is lost)
in case the money is lost, show an icon that once clicked will ask the user if he wants to recount the following days daily budget
today's budget status in % and money equivalent
this month's budget status in % and money equivalent

## History, Statistics page
a date should just go here
no need for showing this, it should be just showed once. At the top
add an expense button should also go here

## Add Expense
fields | all fields must be editable
date
amount
category
description
payment method

## Monthly Budget
pop up to set the budget for all months
window pop up to set the budget for the month